## Project Overview
PROJECT OVERVIEW
|  |  | June |  |  |  | May
|  |  | June | [7 empty] | June
|  | Days | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Sprint | Activity | Progress
1 - HOMEPAGE | Design/Development
| Wireframe/Prototype Design | 100%
| Visual Design | 100%
| Front-End Production | 100%
| Copywriting | 100%
| Analytics | 100%
| Back-End Development | 100%
| Integration with REST services | 100%
| TDD | 100%
2 - HOMEPAGE WITH LOGGED USER | Development
| Wireframe/Prototype Design | 100%
| Visual Design | 100%
| Front-End Production | 100%
| Copywriting | 100%
| Analytics | 100%
| Back-End Development | 100%
| Integration with REST services | 100%
| TDD | 100%
3 - CONTACT US | Development
| Wireframe/Prototype Design | 100%
| Text Boxes | 100%
| Form | 100%
| Buttons | 100%
| Front-End Production | 100%
| Back-End Development | 100%
4 - ABOUT US | Development
| Wireframe/Prototype Design | 100%
| Writing about us | 100%
| Writing about our jobs | 100%
| Writing about the Lab | 100%
| Front-End Production | 100%
| Back-End Development | 100%
5 - F.A.Q. | Development
| Wireframe/Prototype Design | 100%
| Writing Help Section | 100%
| Writing common questions | 100%
| Front-End Production | 100%
| Back-End Development | 100%
6 - SIGN UP AND LOGIN | Sign up
| Wireframe/Prototype Design | 100%
| Text Boxes | 100%
| Buttons | 100%
| Front-End Production | 100%
| Back-End Development | 100%
Login
| Wireframe/Prototype Design | 100%
| Text Boxes | 100%
| Buttons | 100%
| Front-End Production | 100%
| Back-End Development | 100%
7 - PASSWORD RESET | Development
| Wireframe/Prototype Design | 100%
| Text boxes | 100%
| Buttons | 100%
| Front-End Production | 100%
| Back-End Development | 100%
8 - OFFLINE WEBSITE | Development
| Wireframe/Prototype Design | 100%
| Writing a message | 100%
| Front-End Production | 100%
| Back-End Development | 100%

## Daily Planning
Task Estimation |  |  |  |  | Daily Planning
|  | Estimates (hours) |  |  |  |  | Daily Work |  | Total Balance
User Stories | Task | UX | Back-End Development | Front-End Production | Day | Date | Planned | Actual | Planned | Actual | Notes
1 | Sign up | 0 | 2 | 2 | 0 | 2017-06-23 | 0 | 0 | 156 | 156
2 | Log in | 0 | 1 | 1 | 1 | 2017-06-24 | 7 | 8 | 149 | 148
3 | Log out | 0 | 1 | 1 | 2 | 2017-06-25 | 0 | 0 | 149 | 148
4 | Password reset | 0 | 2 | 2 | 3 | 2017-06-26 | 9 | 9 | 140 | 139
5 | Change username | 0 | 1 | 1 | 4 | 2017-06-27 | 9 | 9 | 131 | 130
6 | Change e-mail | 0 | 1 | 2 | 5 | 2017-06-28 | 9 | 9 | 122 | 121
7 | Change password | 0 | 1 | 1 | 6 | 2017-06-29 | 9 | 11 | 113 | 110
8 | Delete account | 0 | 2 | 2 | 7 | 2017-06-30 | 9 | 9 | 104 | 101
9 | Visualizing username in homepage | 0 | 1 | 2 | 8 | 2017-07-01 | 7 | 9 | 97 | 92
10 | Mailing list subscription | 0 | 2 | 1 | 9 | 2017-07-02 | 0 | 0 | 97 | 92
11 | Encryption key insertion | 0 | 1 | 1 | 10 | 2017-07-03 | 9 | 8 | 88 | 84
12 | Encryption key generator | 0 | 2 | 2 | 11 | 2017-07-04 | 9 | 8 | 79 | 76
13 | Encryption key tips | 3 | 1 | 2 | 12 | 2017-07-05 | 9 | 9 | 70 | 67
14 | Encryption key tester | 0 | 2 | 2 | 13 | 2017-07-06 | 9 | 9 | 61 | 58
15 | Message's characters limitator | 0 | 1 | 1 | 14 | 2017-07-07 | 9 | 9 | 52 | 49
16 | Message's characters counter | 0 | 1 | 1 | 15 | 2017-07-08 | 7 | 8 | 45 | 41
17 | Message's decryption time-out | 0 | 2 | 2 | 16 | 2017-07-09 | 0 | 0 | 45 | 41
18 | Message's downloader | 0 | 1 | 1 | 17 | 2017-07-10 | 9 | 8 | 36 | 33
19 | Message's uploader | 0 | 1 | 1 | 18 | 2017-07-11 | 9 | 8 | 27 | 25
20 | Encryption algorithm | 0 | 10 | 2 | 19 | 2017-07-12 | 9 | 9 | 18 | 16
21 | Decryption algorithm | 0 | 10 | 2 | 20 | 2017-07-13 | 9 | 8 | 9 | 8
22 | QR Code generator | 0 | 10 | 2 | 21 | 2017-07-14 | 9 | 8 | 0 | 0
23 | QR Code: message transfer | 0 | 10 | 1 | 22 | 2017-07-15 | 0 | 0 | 0 | 0
24 | QR Code downloader | 0 | 1 | 1
25 | QR Code uploader | 0 | 1 | 1
26 | F.A.Q. section | 3 | 3 | 2
27 | About Us section | 3 | 3 | 2
28 | Contact Us section | 3 | 3 | 2
29 | Admin's advice if website is down
30 | Admin's users deletion | 0 | 2 | 1
31 | Admin's users modification | 0 | 3 | 2
32 | Admin's users ban | 0 | 2 | 1
33 | Admin's website suspending | 3 | 1.5 | 3
34 | Admin's website activation | 0 | 1.5 | 1
35 | Admin's newsletter sending | 0 | 2 | 1
| Total Planned | 15 | 89 | 52